Chrystalls Stopbank Upgrade

Summary of Estimated Costs Following Receipt of Tenders

STAGE 1 : DESIGN, CONSENTS, LAND PURCHASE
AND CONSTRUCTION

(REPORT PE 99.648)

| ##### 1998/99 | ###### Budget | ###### Actual | ###### Difference |
| --- | --- | --- | --- |
| Land access negotiations, legal and survey fees etc. | 13,050 | 7,445 | 5,605 |
| Design and Consents | 52,450 | 57,794 | (5,344) |
| Land Purchase | 18,000 | 0 | 18,000 |
| ##### Subtotal | $83,500 | ###### $65,239 | $18,261 |
| ##### 1999/2000 |  | ###### Estimated |  |
| Engineering Consultants | 0 | 42,000 | (42,000) |
| WRC Staff input | 15,404 | 8,000 | 7,404 |
| Contingency | 0 | 10,000 | (10,000) |
| Construction (incl. $30,000 contingency) | $466,496 | 222,007 | 244,489 |
| Environmental Enhancement |  | 20,000 | (20,000) |
| Land access negotiations, legal and survey fees etc. | 0 | 17,000 | (17,000) |
| Land Purchase | 0 | 35,000 | (35,000) |
| ### Subtotal | $481,900 | $354,007 | $127,893 |
| # Stage 1 Total | $565,400 | $419,246 | $146,154 |

STAGE 2 : LAND PURCHASE

| 1999/2000 |  | ###### Estimated |  |
| --- | --- | --- | --- |
| Land access negotiations, legal and survey fees etc. | 0 | 7,000 | (7,000) |
| Land Purchase | 0 | 93,000 | (93,000) |
| ### Total |  | $100,000 | ($100,000) |

TOTAL

|  | ###### Budget | ###### Estimated | ###### Difference |
| --- | --- | --- | --- |
| INCLUDING STAGE 2 LAND | $565,400 | $519,246 | $46,154 |

## Budget Summary

1998/99 Design and Consents	$  65,500

1998/99 Asset Purchase	$  18,000

1999/2000 Construction	$481,900